## Backlog
ID | Item | Sprint | Assignee
1 | Write a concise purpose statement for the project | 1 | Troy
2 | Decide on a set of high-level entities, and describe their relationships | 1 | Everyone
3 | Create an interaction Diagram to describe the interactions of the high-level entities | 1 | Everyone
4 | Describe the interactions in that diagram with descriptions and UML | 1 | Troy, McLain, Abdul
5 | Establish the risks, benefits, and assumptions of the project | 1 | Marshall
6 | Set up framework code based on the UML diagram to allow team members to fill in implementations | 2 | Troy
7 | Splash screen appears when program begins | 2 | Troy
8 | Splash screen includes a (somewhat working) blinking "ENTER" button | 2 | Troy
9 | Splash screen displays instructions upon being entered on a new screen | 2 | Troy
10 | Next screen allows user to choose how many pancakes to stack | 2 | McLain
11 | Same screen allows user to set the difficulty of their opponent | 2 | McLain
12 | Handle incorrect difficulty input | 2 | McLain
13 | Allow user to choose an order for the pancake stacks before the game or choose a random order | 2 | Marshall
14 | Validate user order or use C++ STL to shuffle the pancakes | 2 | Marshall
15 | Allow player to enter their initials on the next screen | 2 | Abdul
16 | Allow player to see the high scores loaded from the file on that same screen | 2 | Abdul
17 | Draw one pancake | 3 | Marshall
18 | Draw a stack of pancakes in its own window | 3 | Marshall
19 | Draw another stack of pancakes in a separate window without affecting the other stack | 3 | Marshall
20 | Allow user to make a selection using arrow keys | 3 | McLain
21 | Access a data structure containing the pancake draw instructions for each pancake and print them individually | 3 | McLain
22 | Blink those pancakes above and including the selected pancake for 3 seconds | 3 | McLain
23 | Print the updated user stack to reflect changes | 3 | McLain
24 | Calculate the AI's move by performing a minimax tree depth search | 3 | Troy
25 | Blink the pancakes at and above the AI's choice for the player | 3 | Troy
26 | Execute the AI's move by flipping the pancakes above that choice and redraw the AI's stack | 3 | Troy
27 | When the game is over, calculate the user's score | 3 | Abdul
28 | Generate a new screen to show the user their score | 3 | Abdul
29 | On the same screen, display the previous scores read from the file, with all 6 scores sorted | 3 | Abdul
30 | Write the scores to the file, and ask the user if they would like to play again or quit | 3 | Abdul
31 | Make sure the user cannot mess up the first splash screen or instructions screen | 4 | Troy
32 | Handle illegal pancake selections | 4 | McLain
33 | Show the user their difficulty before leaving second screen | 4 | McLain
34 | Handle incorrect pancake stack orders | 4 | Marshall
35 | Show pancake stack order when leaving third screen | 4 | Marshall
36 | Cleanly display results on scores screen | 4 | Abdul
37 | Display only 5 results plus user's 0 score on same screen | 4 | Abdul
38 | Fix any issues that arise when users try our game | 5 | Everyone

## Burndown
Date | Items Due | Items Completed | Items Due Count (running total) | Completed Count (running total) | Planned | Actual
2018-11-08 |  |  | 0 | 0 | 38 | 38
2018-11-11 | 1 | 1,2 | 1 | 2 | 37 | 36
2018-11-12 | 2 | 3 | 2 | 3 | 36 | 35
2018-11-13 | 3 | 4,5 | 3 | 5 | 35 | 33
2018-11-14 | 5,4 |  | 5 | 5 | 33 | 33
2018-11-15 | 6,8,9,10 | 6,7,8 | 9 | 8 | 29 | 30
2018-11-18 | 7,11,12,13,14,15,16,17 | 9,10,11,15,16,17 | 17 | 14 | 21 | 24
2018-11-19 |  | 12,13,14 | 17 | 17 | 21 | 21
2018-11-26 | 18,19,20,21 |  | 21 | 17 | 17 | 21
2018-11-27 | 22,24,25,26 | 18,19,22,23,24 | 25 | 22 | 13 | 16
2018-11-28 | 23,27 | 20,21 | 27 | 24 | 11 | 14
2018-11-29 | 28, |  | 29 | 24 | 9 | 14
2018-12-01 | 29,30,31,33,34,35,36 | 25,26,31,33, | 36 | 29 | 2 | 9
2018-12-02 | 37 |  | 37 | 29 | 1 | 9
2018-12-03 | 38 | 27,28,29,30,32 | 38 | 34 | 0 | 4
|  | Total Tasks: | 38